## Gantt Chart
Beyond Buttons : Rethinking Control |  | Course: | BSc (Hons) Computer Gameplay Design and Production
Alex Wood
| Project Start: | 2024-10-01
| Display Week: | 1 |  |  | 2024-09-30 | [6 empty] | 2024-10-07 | [6 empty] | 2024-10-14 | [6 empty] | 2024-10-21 | [6 empty] | 2024-10-28 | [6 empty] | 2024-11-04 | [6 empty] | 2024-11-11 | [6 empty] | 2024-11-18 | [6 empty] | 2024-11-25 | [6 empty] | 2024-12-02 | [6 empty] | 2024-12-09 | [6 empty] | 2024-12-16 | [6 empty] | 2024-12-23
 | time axis 2024-09-30 to 2024-12-29
TASK | PROGRESS | START | END | WORK DAYS | time axis 2024-09-30 to 2024-12-29
Pre-Production |  |  | -
Create Initial Idea | 100% | 2024-10-01 | 2024-10-04 | 4
First Supervisor Meeting | 100% | 2024-10-04 | 2024-10-04 | 1
Create Proposal Documentation | 100% | 2024-10-07 | 2024-10-11 | 5
Create Gantt Chart | 100% | 2024-10-07 | 2024-10-11 | 5
Supervisor Meeting | 100% | 2024-10-11 | 2024-10-11 | 1
Research |  |  | - | -
Component Research | 0% | 2024-10-14 | 2024-10-17 | 4
Existing Examples | 0% | 2024-10-14 | 2024-10-15 | 2
Resource Collection | 0% | 2024-10-14 | 2024-11-01 | 14
Pre-Development |  |  | -
Arduino Framework | 0% | 2024-10-16 | 2024-11-28 | 30
Unreal Framework | 0% | 2024-10-16 | 2024-11-28 | 30
Prototype 1 |  |  | -
Component Research | 0% | 2024-10-21 | 2024-10-24 | 3
Arduino Development | 0% | 2024-10-23 | 2024-11-05 | 10
Tech Demo Development | 0% | 2024-10-28 | 2024-11-08 | 10
Testing | 0% | 2024-11-06 | 2024-11-08 | 3
Iteration | 0% | 2024-11-08 | 2024-11-12 | 3
Prototype 2 |  |  | -
Component Research | 0% | 2024-11-11 | 2024-11-13 | 3
Arduino Development | 0% | 2024-11-13 | 2024-11-27 | 10
Tech Demo Development | 0% | 2024-11-18 | 2024-12-02 | 10
Testing | 0% | 2024-11-30 | 2024-12-03 | 3
Iteration | 0% | 2024-12-03 | 2024-12-05 | 3
Prototype 3 |  |  | -
Component Research | 0% | 2024-12-09 | 2024-12-11 | 3
Arduino Development | 0% | 2024-12-11 | 2025-01-07 | 10
Tech Demo Development | 0% | 2024-12-16 | 2025-01-10 | 10
Testing | 0% | 2024-12-28 | 2025-01-07 | 3
Iteration | 0% | 2025-01-07 | 2025-01-09 | 3
Post Mortem |  |  | -
Testing | 0% | 2025-01-09 | 2025-01-22 | 10
Feedback Writeup | 0% | 2025-01-23 | 2025-02-05 | 10
Post Mortem Evaluation | 0% | 2025-02-01 | 2025-02-13 | 10
BUFFER | 0% | 2025-02-13 | 2025-02-17 | 3
HAND IN | 0% | 2025-02-18 | 2025-02-18 | 1

## Settings
Weekend Option
| Weekend String | 0000011
| Monday | 0
| Tuesday | 0
| Wednesday | 0
| Thursday | 0
| Friday | 0
| Saturday | 1
| Sunday | 1
SameDay Start
| Yes | 1
| No | 0

## Holidays
Holidays and Other Non-Work Days
Date | Description
2024-12-25 | Christmas Day
2024-12-21 | Christmas Holidays
2024-12-22 | Christmas Holidays
2024-12-23 | Christmas Holidays
2024-12-24 | Christmas Holidays
2024-12-25 | Christmas Holidays
2024-12-26 | Christmas Holidays
2024-12-27 | Christmas Holidays
2024-12-28 | Christmas Holidays
2024-12-29 | Christmas Holidays
2024-12-30 | Christmas Holidays
2024-12-31 | Christmas Holidays
2025-01-01 | Christmas Holidays
2025-01-02 | Christmas Holidays
2025-01-03 | Christmas Holidays
2025-01-04 | Christmas Holidays
2025-01-05 | Christmas Holidays
2024-11-26 | Module Submission Date
2025-02-18 | Module Submission Date
2024-10-23 | Ukie Conference

## Courses
Courses
BSc (Hons) Computer Games Design and Programming
BSc (Hons) Computer Games Design
BSc (Hons) Computer Games Design with Animation
BA (Hons) Games Art (with a foundation year)
BA (Hons) Concept Art for Games and Film (with a foundation year)
BSc (Hons) Computer Gameplay Design and Production
BA (Hons) Concept Art for Games and Film
BA (Hons) Games Art
BSc (Hons) Computer Gameplay Design and Production (with a placement year)
BSc (Hons) Computer Games Programming
BSc (Hons) Computer Games Development
BSc (Hons) Computer Games Design (with a placement year)
BSc (Hons) Computer Games Programming (with a foundation year)
BSc (Hons) Computer Games Design with Animation (with a foundation year)
BSc (Hons) Computer Games Programming (with a placement year)
BSc (Hons) Computer Games Design and Programming (with a foundation year)
BSc (Hons) Computer Games Design and Programming (with a placement year)
BSc (Hons) Computer Games Design (with a foundation year)
BSc (Hons) Computer Gameplay Design and Production (with a foundation year)
BSc (Hons) Computer Games Development (with a placement year)
BSc (Hons) Computer Games Design with Animation (with a placement year)
BSc (Hons) Computer Games Development (with a foundation year)